(Translation)

For Information 









  WCDC Paper

On 15.7.2008  









  No.: 87/2008

Progress Report of the 4th Meeting 

District Works and Facilities Management Committee

3rd Wan Chai District Council


The District Works and Facilities Management Committee (DWFMC) held its 4th meeting on 24 June 2008 respectively and discussed the following issues:

1.
Progress Report of District Works Project

(I) Beautification Project of the Public Place under Canal Road Flyover

Mr. CHAN of Urban Age International Ltd, Architects, expressed that the revised project budget proposal had been submitted to the Works Section of Home Affairs Department for consideration.  The Works Section requested them submitting supplementary information in due course.  Based on the present estimate, they could invite tender in August and award the tender in October.  The construction would take about 6 months and complete in April 2009.

(II) Bridging Arts: Public Art Design Project

Representative of consultancy firm expressed that the design, W-Design, could invite tender while there were some technically unsolved problems for the designs, Hong Kong Timeline and Paper Lantern Bridge.  Hence, tendering procedures could not commence.  In view of the rising construction price, the Committee worried that implementation of the whole project would be hindered.  After careful consideration, the Committee agreed W-Design alone going into tendering process.

(III)
Rain Shelters Projects in Bowen Road and Wan Chai Gap Road
Consultancy Firm had received tender applications for the above two projects at Bowen Road and Wan Chai Gap Road.  They were now analyzing and scrutinizing the content of the tender documents.  It was estimated that the two works could formally commence in July.  The projects in Bowen Road and Wan Chai Gap Road would take 120 days and 60 days respectively.

2. Meeting with Contract Project Consultants

7 representatives from Associated Architects Ltd, which had been awarded the Consultancy Contract for District Minor Works in Islands for 2008/2010, attended the meeting.  During the meeting, the consultancy firm briefed members on their work and the experience of implementing the district minor works in collaboration with the government.  The consultancy firm expected to maintain closer contact with the Committee and to assist the Committee in fostering improvement of community facilities.

3. Reviewing the Arrangement of setting Up Designated Smoking Areas in Public Pleasure Grounds by Leisure and Cultural Services Department

The Leisure and Cultural Services Department proposed to maintain the arrangement of setting up designated smoking areas in 86 public leisure grounds in Wan Chai District.  The proposal was approved by the Committee.

4.
Position of District Minor Works Funds
The Committee approved at this meeting the grant of $844,000 for 6 improvement works of community facilities. Presently, the Committee had committed to a project budget of $14,221,000. 

5.
Applications for WCDC Funds

The Committee approved at this meeting the grant of $844,000 for 3 applications for 6 District Minor Works, including, (1) 2008/09 Anti-blockage Scheme of Community Facility Drains; (2) Wan Chai District Leisure and Sports Facilities Improvement Project 2008/09 (Phase 2) by Leisure and Cultural Services Department; and (3) Addition of 2 Chess Boards at Lockhart Road Playground.

Wan Chai District Council Secretariat

July 2008
PAGE  
1
3rd Term_DWFMC_4 pr.doc


